## Communications Guide
Communications Guide
Introduction | The Communication Plan contains communications activities and events for all internal and external stakeholders impacted by the project
Timing | The communications Plan should be developed during the Planning, Analysis and Design Phase of PMLC
Communication Plan | The Communications Plan outlines project key messages, branding and visual identity considerations, stakeholder needs, and planned communications events and activities.
Messaging | Key messages are the three or four most important statements about a project the team wishes to share with stakeholders. They should communicate both key facts and motive. Depending on the project, it may be important to both repeat some key messages over the life of the project, and introduce new messages as the project evolves.
Executive Staff | Recommend use External Relations and have Executive Sponsor Approval
Company | Recommend use External Relations and have approvals from Executive Sponsor, Project Manager and/or Chief Executive Office's Office
Staff | Recommend use External Relations and have approval from Executive Sponsor
Client | Recommend use External Relations and have approvals from Executive Sponsor and Chief Executive Officer's Office
External Stakeholders | Recommend use External Relations and have Executive Sponsor Approval
Messaging Medium | Some types of Communication have specific sign-off and requirements, see infomail as an example (Github, Website, e-mail, PowerPoint)
Infomail Protocol and Guidelines | Provides an overview of protocols and guidelines as related to distribution of mass emails to company, staff, client and seller. Lead time, required sign-offs, and general information is in this guide
Branding and Visual Identity | All branding and visual identity must confirm to the GW standards. Contact External Relations for guidelines.
Budget | ALL communications developed are constrained by the communications budget. As an example, If the project sponsor plans to communicate via printed materials using the USPS, the PM must contact external relations to get quotes for the printed material and related expenses. The lead time for this varies by the type of printed material.

## Communications Sample Entries
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Client | Reviewer | Company / Staff | Person In-charge
1
| Name of the Communications Piece | Medium | Delivery Date | Frequency | Briefly describe the content of the communication piece | Person(s) who will receive the communication | Person(s) who will review and approve the communications piece | Company/Staff/Client | Person(s) responsible for document
| Examples: | Examples: | on-going | daily | CCTV needed for installation; company do not make this hardware | Company | IT Director | Company | External Relations -Ain
| Reminder emails to Finance Staff | email | specific Date | weekly | Find service company to configure the CCTV at the housing area | Staff | Executive Sponsor | Staff | IT Communications - Ain
| Letter to Retirees re: benefit changes in 2012 | USPS Printed Letter |  | one-time | Service for transferring data to CCTV; company do not have the skill for installation | Client | IT Project Manager | Client | FSS - Izzati
| email to Executive Staff | 4 color Process Print |  | quarterly | Reseach for internet service | IT Project Manager | Vice President |  | KPIs - Megala;Izzati
| email to School of Business Faculty | Flyer |  | yearly | Google Clouds service for storage, big data, can be used for cloud AI. | System Designer | Executive Staff
| Memo to Faculty | meeting |  | bi-monthly |  | Programmer
|  | logo |  |  |  | IT Help Desk
|  | website |  |  |  | Business Analyst
survey
promotional piece
campus mail
infomail
GW Today
Advertising
phone
training session
memo
meeting
ITSM Ticket

## Merit Project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Client | Reviewer | Company/ Staff | Person In-charge
1 | Project Team Communication | Online Meeting | Ongoing | Weekly | Weekly status meeting to discuss schedule, communications, actions, risks & issues | Project Team | Megala | Staff | Izzati
2a | Executive Sponsor Communication | PPT | Ongoing | Weekly | Weekly status report to executive sponsors for overview of the project progress | Executive Sponsor - Muhammad Ariff | Megala, Ain | Staff | Izzati
2b | Executive Sponsor Communication | online Meeting | Ongoing | Monthly | Monthly executive overview of the project progress | Executive Sponsor - Muhammad Ariff | Megala, Ain | Staff | Izzati
3 | FORMAL: Merit percentage notification, range notification, basic merit guidelines (Vice President, IT Director, Executive Staff) | Letter | 2020-09-10 | One-time |  | To IT Project Manager | Ain | Staff | Izzati
4 | Tech-Solution & all Executive & responsibility | Email | 2020-09-13 | One-time | Create list of responsibilities for merit liaisons (e.g. communicate appropriate information to supevisors, dept heads, AVP's etc.) | IT Department & all employees | Magala | Staff | Izzati
5 | Communication to departments regarding grade minimums. | Email | 2020-09-15 | One-time | Will include instructions on ways to notify employees. | IT Department & all employees | Megala | Staff | Izzati
6 | FORMAL: Merit percentage notification, range notification, basic merit guidelines (Tech-Solution & all Executive. | Letter | 2020-09-15 | One-time | Same document as #5 but with a bit more data. | IT Department & all employees | Megala | Staff | Izzati
7 | Company merit guidance | Letter | 2020-09-15 | One-time | Describes merit pool, any holdback, etc. | IT Project Manager | Megala | Company | Ain
8 | Creation and distribution of letters to employees impacted by grade minimum change | N/A | 2020-09-20 | One-time |  |  | Megala | Staff | Ain
9 | FAQ's | Webpage | 2020-09-30 | One-time | Can't finish web page until we have clarification from on dates. | Fusion Tech Staff | Ain, Izzati | Staff | Megala
10 | Create additional webpage content | Webpage | 2020-09-30 | One-time | Can't finish web page until we have clarification from on dates. | Fusion Tech Staff | Ain, Izzati | Staff | Megala
11 | Placed all of the project updates in the github. | Github | Ongoing | Monthly | Monthly status report to Project Manager and Exectutive for overview of the project update | Fusion Tech Staff | Megala, Ain | Staff | Izzati
12 | Final approval of merit increases | Email | 2020-12-08 | One-time | All merit increases have been approved based on final submission of data. You may notify employees starting XX and after package date. | Tech-Solution & all Executive | Ain, Izzati | Staff | Izzati
13 | Merit Packages | Letter | 2020-12-08 | One-time | Decision being made if this will be templates or actual packages. If templates, the date will have to be moved up. | Tech-Solution & all Executive | Megala, Izzati | Staff | Ain
14 | Creation of merit worksheet guidance (first tab of merit workbooks) | XLS |  | One-time |  |  |  | Staff
15 | Reminder emails to merit liaisons to return final spreadsheets on or before 11/15 | XLS | 10/28, 11/3, 11/9, 11/15, | Every 4 days until s/s returned | Mitigation for risk of late spreadsheets | Tech-Solution & all Executive | None | Staff | Ain